## Slide 1
ORACLE 19.30 EE FLEET · AIX 7.2 / POWER · NON-RAC · DATA GUARD
Encrypting the Oracle Fleet
TLS in transit & TDE at rest
A fleet-wide programme to close the cleartext-network and unencrypted-datafile findings — two independent, parallel security tracks with runbooks, script templates and a phased rollout.
Programme overview · 30 minutes
Notes: Set the frame: this is a greenfield rollout of two encryption controls across a large Oracle 19c estate. No TLS and no TDE anywhere today. Both are regulatory-driven (DORA, PCI). The key message I'll repeat: TLS and TDE are run as two separate tracks. ~30 minutes, roughly half TLS, half TDE, then rollout and actions.

## Slide 2
HOW THIS SESSION IS STRUCTURED
Agenda
1
Programme context
Drivers, environment, the two-track principle
2
TLS — data in transit
What it is · what's built · lessons · actions
3
TDE — data at rest
What it is · key management · what's built · actions
4
Rollout & next steps
Wave model, pilot, consolidated action points
Notes: Quick roadmap. I'll spend a couple of minutes on shared context, then go deep on TLS, then TDE, then close with the rollout plan and the concrete actions I need from this group. If you only remember one structural point: these are two independent workstreams that happen to run at the same time.

## Slide 3
WHY NOW, AND WHAT WE'RE WORKING WITH
Programme context
Drivers
DORA Encryption of data at rest & in transit; demonstrable key management and resilience
PCI-DSS-style Sensitive data encrypted on the wire and rendered unreadable at rest; documented key lifecycle
Bank security policy Confidential data encrypted; separation of duties for key custody; auditable crypto
Audit / regulator findings Cleartext SQL*Net and unencrypted datafiles are recurring findings — closed fleet-wide
The estate
19.30 EE
Enterprise Edition, non-RAC single-instance
AIX 7.2
IBM POWER — crypto path differs from x86 AES-NI
CDB + non-CDB
Mixed architecture; keystore handling differs
Data Guard
Physical standby on almost every database
Greenfield
No TLS and no TDE anywhere today
ASO licensed
Covers TDE · OKV would be a separate purchase
Notes: Frame the constraints that shape every decision downstream. Two matter most technically: AIX on POWER, because the crypto acceleration story is different from x86 and we must measure TDE overhead rather than assume it; and Data Guard everywhere, because wallet sync and encrypted redo apply drive both tracks. Licensing: ASO is already paid for, so TDE has no cost barrier — OKV is a separate business case we'll come to.

## Slide 4
THE ORGANISING PRINCIPLE
Two independent, parallel tracks
TRACK A
TLS / TCPS
Touches: listener · certificates · client connect strings
wallet + cert
listener dual-port
migrate clients
close TCP 1526
Fully reversible · no data impact
TRACK B
TDE
Touches: keystores · master keys · tablespaces
WALLET_ROOT
keystore + MEK
standby sync
encrypt tbs
Plan as forward-only · keys forever
Separate change windows, separate rollback, separate acceptance criteria. Coupling them multiplies risk and blast radius. A database can be TLS-done while TDE is still in progress — or the reverse.
Notes: This is the single most important design decision, so I give it its own slide. TLS and TDE share almost nothing operationally. If we bundle them into one change we double the blast radius and make rollback ambiguous. Note the asymmetry at the bottom of each card: TLS is fully reversible during coexistence; TDE must be planned as forward-only because any backup taken after encryption needs the key forever. Keep that distinction in mind for the rest of the deck.

## Slide 5
SECTION 1
TLS — data in transit
Encrypting SQL*Net with TCPS and authenticating the server against the internal CA
What & why
Design decisions
What's built
Lessons learned
ANO interim
Action points
Notes: Now the TLS track. I'll cover what TLS gives us versus what we have today, the key design choices, exactly what's been built in the runbook and scripts, the pitfalls we hit and verified live, the native-encryption interim option, and then the actions.

## Slide 6
INTRODUCTION TO THE TOPIC
TLS: what it is and why
TODAY
Cleartext SQL*Net
TCP on port 1526 only
No server certificates
No identity, no MITM protection
TARGET
TLS / TCPS
TCPS on port 1527, AES-GCM
Per-host cert from internal CA
Client verifies server identity
Scope
One-way TLS
Server authentication only. Clients validate the server cert; the server does not require client certs.
Mutual-TLS is out of scope.
Dual-port coexistence is the delivery mechanism
One listener serves both TCP 1526 and TCPS 1527 simultaneously. Existing clients keep working on 1526 while each application team migrates its connect strings, truststores and pools to 1527 at its own pace. Only when monitoring shows zero remaining cleartext sessions do we close 1526. This decouples DBA-side enablement from app-side migration — the biggest schedule risk on this track.
Notes: The 'what': TLS encrypts the SQL*Net wire AND authenticates the server via a CA-issued certificate — that second half is what native encryption can't give us, and what regulators increasingly expect. The 'how' at the bottom is dual-port coexistence: we don't do a big-bang cutover. We stand up 2484 alongside 1521 and let apps move one at a time. The gate to close 1521 is evidence of zero cleartext sessions.

## Slide 7
THE STANDARD WE'VE FIXED
TLS design decisions
Dual-port
TCP 1526 kept during coexistence; TCPS added on 1527
One-way TLS
SSL_CLIENT_AUTHENTICATION = FALSE — server auth only
TLS 1.2 default
Fleet 19.30 supports 1.3 — enable after client-driver check
Strong ciphers
ECDHE + AES-GCM only (forward secrecy); no CBC / RSA-kx
3072-bit RSA
CN = server FQDN; SANs for every name clients use
Separate wallet
TLS wallet never shared with the TDE keystore
Notes: These are the conventions baked into the scripts so every DB is configured identically. The two I'd flag to a security reviewer: we pin TLS 1.2 by default because native 1.3 support in the DB stack only landed around 19.23 and can fail the handshake on lower RUs — we enable 1.3 per host only after verifying. And the wallet separation rule: TLS certificates and TDE master keys live in different wallets, different directories, different lifecycles. Never merged.

## Slide 8
DELIVERABLES ON THIS TRACK
TLS — what's built
Wallet & CSR workflow
orapki: create, CSR, import chain in the right order
Listener & sqlnet.ora
TCPS endpoint, wallet, ciphers, DN-match, registration
JDBC thin clients
JKS truststore with the CA root — wallet-free, ranked options
Legacy OCI clients
Trust-anchor-only auto-login wallet + tnsnames
APEX / ORDS
TCPS pool URL + ORDS JVM truststore
DB links over TCPS
DB-as-client already trusts peers via the shared CA
Data Guard redo
TCPS transport + static registration for role changes
Rotation & monitoring
Zero-downtime renewal; T-45/30/14 expiry alerts
SCRIPTS
scripts/tls/ 01 wallet+CSR · 02 listener/sqlnet/tns fragments · 03 TCPS verification (.sql + .sh)
Notes: This is the coverage of the TLS runbook plus the script templates. The point I want to land: it's not just 'turn on TCPS on the server' — the whole client surface is documented. Java thin via a JKS truststore is the recommended, wallet-free path. OCI, ORDS, DB links and Data Guard redo transport each have their own recipe. Rotation is zero-downtime for the listener via lsnrctl reload, with expiry monitoring so a cert never lapses silently. Everything is backed by the three tls scripts.

## Slide 9
HARD-WON, VERIFIED LIVE ON 19C
TLS pitfalls that will bite
sqlnet.ora needs the wallet too
Wallet only in listener.ora → clients get ORA-28865 after a good handshake. The spawned DB server process re-reads sqlnet.ora and needs WALLET_LOCATION there as well.
One WALLET_LOCATION only (SEPS clash)
sqlnet.ora supports a single WALLET_LOCATION. If SEPS / WALLET_OVERRIDE already exists, appending a second one silently breaks one of them. Audit fleet-wide; merge, don't append.
orapki CSRs carry no SANs
19c orapki generally omits SANs. Have the CA template stamp CN=FQDN + DNS SANs, or build the CSR with openssl. Otherwise DN-match fails from some clients.
New endpoint ≠ reload
Adding the TCPS ADDRESS needs a full lsnrctl stop/start — reload is not enough. (Cert renewal into the same wallet IS picked up by reload.)
Notes: These four cost real time in testing, and they're now written down so no one on the fleet re-discovers them. The first is the classic: everything looks configured, the handshake succeeds, then the session dies with ORA-28865 — because the dedicated server process, not the listener, holds the session up and it reads sqlnet.ora. The SEPS conflict is a landmine on Data Guard hosts that already use a password store. These were verified live, not theory.

## Slide 10
A PRAGMATIC INTERIM CONTROL
Native encryption (ANO) while TLS lands
The quick win
Free since 2013. Native SQL*Net encryption was de-licensed — no ASO, no licence needed. (TDE still requires ASO.)
Zero client change.
Set the server side alone and any 19c-era JDBC-thin / OCI client negotiates AES256 with no client config.
SQLNET.ENCRYPTION_SERVER = REQUIRED
SQLNET.ENCRYPTION_TYPES_SERVER = (AES256)
Closes the “cleartext on the wire” finding quickly and cheaply.
Not a substitute for TLS
Encrypts the wire — Yes — AES256
Server authentication — No — client can't verify identity
MITM protection via PKI — No
Audit control fully met — Partially (encryption only, no auth)
Recommendation: use as a short-lived interim, then supersede with TLS. Skip it if TLS lands on an acceptable timeline. Do not treat it as the end state.
Notes: A pragmatic point for the sponsors. Migrating hundreds of connect strings takes months. Native network encryption is free and needs only a server-side change to encrypt every session in AES256 — it closes the cleartext finding almost immediately. But it authenticates nothing, so it is explicitly an interim, not the destination. If TLS can move fast enough we skip it entirely; otherwise it buys us cover while the PKI work proceeds.

## Slide 11
WHAT WE NEED TO PROCEED
TLS — action points
1
CA & certificate process
Confirm the internal CA can issue with CN=FQDN + DNS SANs via a template, and agree the CSR turnaround SLA.
2
Pre-flight the fleet
Audit every sqlnet.ora for an existing WALLET_LOCATION / SEPS override before we touch it (grep -c WALLET_LOCATION).
3
Firewall 1527
Open TCPS 1527 from all client subnets and between primary ↔ standby; keep 1526 open during coexistence.
4
Decide on ANO interim
Sponsor call: enable native encryption now as a quick win, or wait for TLS?
5
App-team engagement
Start truststore + connect-string migration early — it is the long pole; provide the CA root and per-app instructions.
6
Expiry monitoring
Stand up cert-expiry alerting (OEM / openssl probe) before any TCPS endpoint goes live.
Notes: The concrete TLS asks. Two are dependencies on other teams and are on the critical path: the CA process must support SANs, and app teams must start migrating early because that's the long pole. The sqlnet.ora audit is cheap insurance against the SEPS landmine. And we need a sponsor decision on whether to switch on native encryption as an immediate stopgap.

## Slide 12
FREQUENTLY ASKED — TLS TRACK
TLS FAQ — design & setup
1
Do we need an outage to add TLS?
No — dual-port coexistence. Only adding the new 1527 endpoint needs a full listener stop/start.
2
Is this mutual TLS? Client certs?
No — one-way, server-auth only. Clients just need the CSOB CA chain in a truststore.
3
Where does the TLS wallet live?
In /oracle/admin/$SID/wallet_tls — kept strictly separate from the TDE keystore.
4
Which auto-login wallet type?
Plain -auto_login. Avoid -auto_login_local: it's host-bound and won't open after a DR move.
5
Pin TLS 1.2 or allow 1.3?
Fleet on 19.30 supports 1.3. Keep 1.2 as the default until client drivers are validated, then allow 1.3.
6
Enable native (ANO) encryption too?
Not on TCPS — it double-encrypts. Use ANO only as the interim control on the surviving 1526.

## Slide 13
FREQUENTLY ASKED — TLS TRACK
TLS FAQ — gotchas & clients
1
Handshake OK, then ORA-28865?
The wallet must be in sqlnet.ora too — the DB server process re-reads it, not just the listener.
2
We use SEPS — will TLS break it?
sqlnet.ora allows one WALLET_LOCATION. Merge the CA trust in — never append. Grep the fleet first.
3
orapki CSR carries no SANs?
Have the CA template stamp CN=FQDN + DNS SANs, or build the CSR with openssl.
4
DN-match fails from some apps?
Set ssl_server_dn_match=true explicitly; the connect host must equal the cert CN and a SAN.
5
What do JDBC-thin apps need?
A JKS truststore with the CSOB root + intermediate — no Oracle wallet or pki jars.
6
Does DG redo need mutual TLS?
No — password-file auth. Add static registration so the standby's 1527 is reachable when MOUNTED.

## Slide 14
SECTION 2
TDE — data at rest
Transparent Data Encryption on tablespaces, backups and Data Guard redo — with keys we can never lose
What & why
Key-management decision
What's built
Conversion methods
Validation & caveats
Action points
Notes: Now the TDE track — data at rest. The stakes here are different from TLS: TLS is reversible and low-risk; TDE is forward-only and the keys are catastrophic to lose. So key management gets its own decision slide.

## Slide 15
INTRODUCTION TO THE TOPIC
TDE: the two-tier key hierarchy
Keystore
MEK — master key
Lives outside the DB
(software wallet now → OKV later)
wraps
Datafile header
DEK — tablespace key
Wrapped (encrypted) by the MEK
Travels with the data
wraps
Data blocks
AES256 ciphertext
DEK encrypts every block
on its way to / from disk
Lose the keystore → lose the data
No MEK means the wrapped keys can't be unwrapped. No back door. Backup & custody are the highest-stakes part of the programme.
Rotating the MEK does NOT re-encrypt data
It only re-wraps the data keys — fast, low-I/O. But old MEKs must be kept forever: old backups and archived redo need them.
Notes: The mental model for TDE is two tiers. The data keys — one per tablespace — live inside the datafile headers and actually encrypt the blocks. The master key lives outside the database in the keystore and only wraps those data keys. That's the whole reason key management is separate: the data keys travel with the data, but the master key is the crown jewel. Two consequences drive every operational rule: lose the keystore and the data is gone, no exceptions; and rotating the master key is cheap because it re-wraps, it doesn't re-encrypt — but you can therefore never delete an old key.

## Slide 16
THE DECISION THAT UNBLOCKS EVERYTHING
Key management: start local, aim for OKV
PHASE 1 — NOW
Local software keystore
Auto-login wallet per DB — no run-time external dependency
Starts the track immediately — no procurement on the critical path
Included in ASO — no new spend
Weak central-evidence story; per-host backup toil at scale
PHASE 2 — TARGET
Oracle Key Vault (multi-master)
Central custody, fleet-wide audit & rotation — the DORA/PCI evidence story
Optional HSM as root of trust
Must be clustered + persistent cache so it's not a fleet SPOF
Separate OKV licence — not yet purchased
Critical enabler — starting local does not block OKV later
Standardise WALLET_ROOT + TDE_CONFIGURATION now, united keystore with per-PDB MEKs, non-local auto-login for Data Guard. Migration to OKV is then a supported, online one-liner per DB (SET ENCRYPTION KEY … MIGRATE USING …) applied wave-by-wave — and it's reversible.
Notes: This is the decision that lets the whole track start. The correct end state for a regulated bank is Oracle Key Vault — central custody, audit, rotation, optional HSM root of trust. But OKV is a separate licence and an appliance we don't have yet. So we start with local software keystores, which are fully compliant as an at-rest control and have no procurement dependency. The critical enabler is at the bottom: because we standardise the WALLET_ROOT conventions now, moving to OKV later is a scripted one-liner per database, not hundreds of bespoke migrations. And it's reversible. So 'start local' is not a trap.

## Slide 17
DELIVERABLES ON THIS TRACK
TDE — what's built
WALLET_ROOT config
01 — static param + restart, TDE_CONFIGURATION=FILE
Keystore + first MEK
02 — create, open, SET KEY, non-local auto-login
Online tbs encryption
03 — generates ALTER statements; run one at a time
Status / verification
04 — keystore + encrypted-tablespace report
MEK rotation
05 — re-wrap keys, tag, WITH BACKUP
Standby wallet sync
dg/ — copy ewallet.p12 + cwallet.sso, verify
ALSO COVERED
United, per-PDB MEKs
One keystore in CDB$ROOT; each PDB keyed separately
Born-encrypted
ENCRYPT_NEW_TABLESPACES = ALWAYS for new tablespaces
Full coverage
SYSTEM / SYSAUX / UNDO / TEMP paths documented
Notes: The TDE deliverable is a five-script SQL chain plus the Data Guard sync helper, matching the runbook order: configure WALLET_ROOT, create the keystore and first key, encrypt tablespaces online, verify, rotate. Note script 03 doesn't auto-run — it generates the ALTER statements for review so we can throttle one tablespace at a time and watch standby lag. The bottom band is the fleet standard: united keystore with per-PDB keys, new tablespaces born encrypted, and documented paths for the system tablespaces so we get full coverage, not just app data.

## Slide 18
PICK PER DB SIZE, DOWNTIME & STANDBY
Four ways to encrypt existing data
Method | Downtime | Redo | DG impact | Best for
1 · Online tablespace encrypt | None | ≈ full tbs size | High | Availability-critical DBs with space + redo headroom
2 · Offline conversion | Yes | Minimal | Low | SYSTEM/SYSAUX/UNDO; the standby step of method 3
3 · Standby-first | Near-zero | Low / side | Managed | ★ Fleet default for large DG-protected databases
4 · Data Pump / RMAN rebuild | Yes | n/a (reload) | Rebuild both | Small DBs, or where a reorg is wanted anyway
Online encryption generates redo ≈ the full tablespace size. On a DG fleet that spikes archive volume, transport and standby apply — pace it one tablespace at a time and size archive + network first.
Notes: Encrypting existing data isn't one method — it's a decision per database. Online is zero-downtime but generates redo equal to the whole tablespace, which on Data Guard means a big transport-and-apply spike. Offline is minimal-redo but takes the tablespace down; it's mandatory for SYSTEM/SYSAUX/UNDO. The starred row, standby-first, is our default for large DG databases: convert the standby offline, switch over, convert the old primary — near-zero downtime and no redo storm. Small databases can just be rebuilt via Data Pump.

## Slide 19
WHAT'S PROVEN, WHAT STILL NEEDS THE FLEET
Validation status & open caveats
Verified live
19.27 Linux CDB test instance · 2026-07-07
Full chain 01 → 02 → online encrypt → 04 → 05 ran end-to-end
United (per-PDB MEK) + isolated both work — FORCE ISOLATE / UNITE verified on 19.27
Non-local auto-login opens OPEN / AUTOLOGIN after restart
FILE_NAME_CONVERT=NONE fails on OMF (ORA-28437) — omit it
CONTAINER=ALL rotation works but leaves keys UNTAGGED
Still open — confirm at fleet RU / on AIX
1
AIX/POWER crypto for TDE — Don't assume free HW acceleration — benchmark overhead in the pilot
2
Standby-first sequencing — Follow the current MOS note for your exact RU
3
UNDO encryption path — Prefer recreate-and-swap regardless of RU
Notes: Honesty slide. The full script chain was executed end-to-end on a 19.27 CDB, so the mechanics are proven — including a couple of real gotchas like FILE_NAME_CONVERT=NONE failing on OMF, and CONTAINER=ALL rotation leaving keys untagged, which matters for audit. What we deliberately have NOT proven is anything AIX- or RU-specific. The big one is performance: POWER's crypto path is different from x86 AES-NI and we must measure, not assume. These four open items feed straight into the pilot.

## Slide 20
WHAT WE NEED TO PROCEED
TDE — action points
1
Key custody & vaulting
Confirm keystore passwords go in the CyberArk-style vault with custody separated from the DBA (PCI/DORA).
2
Keystore backup pipeline
Stand up wallet backups stored separately from DB backups; verify a test-restore. Key = data.
3
Pilot performance baseline
Agree measurements on AIX/POWER: batch elapsed, standby apply rate, RMAN duration, OLTP latency.
4
OKV business case
Decide timing to license + cluster OKV; until then we run standardised local keystores.
5
Encryption scope sign-off
Confirm we encrypt SYSTEM/SYSAUX/UNDO/TEMP too, and set ENCRYPT_NEW_TABLESPACES=ALWAYS.
6
Validate open RU items
Close the four caveats at the fleet's actual RU during pilot before wide rollout.
Notes: The TDE asks. The custody and backup items are non-negotiable — the entire security value of TDE collapses if the key sits next to the ciphertext, or if we lose it. The pilot baseline is how we de-risk the AIX performance unknown. And we need a steer on the OKV business case: we can run compliant on local keystores indefinitely, but the central-audit story only fully arrives with OKV.

## Slide 21
FREQUENTLY ASKED — TDE TRACK
TDE FAQ — keys & multitenant
1
What if I lose the keystore?
Total, unrecoverable data loss — no back door. Wallet backup with separate custody is the #1 control.
2
Does MEK rotation re-encrypt data?
No — it only re-wraps the data keys (fast, low-I/O). And never delete old MEKs.
3
WALLET_ROOT or sqlnet.ora?
Use WALLET_ROOT (static, restart) + TDE_CONFIGURATION (dynamic). Oracle appends /tde itself.
4
Which auto-login on Data Guard?
Non-local AUTO_LOGIN. A LOCAL auto-login is host-bound and won't open on the standby.
5
United or isolated keystore?
United, per-PDB MEK — every RU, one wallet to sync. Isolated only for a PDB that truly needs its own.
6
Can I isolate a PDB on our RU?
Yes — FORCE ISOLATE / UNITE, native on 19.30 (no patch). Verified on 19.27; isolated has no auto-login.

## Slide 22
FREQUENTLY ASKED — TDE TRACK
TDE FAQ — converting & operating
1
Encrypt existing data, least downtime?
Four methods; standby-first is the fleet default for large, DG-protected databases.
2
FILE_NAME_CONVERT=NONE → ORA-28437?
On OMF, omit it entirely — Oracle makes the converted copy in place. Verified on 19.27.
3
DG impact of online encryption?
Redo ≈ the full tablespace size. Pace one tablespace at a time; size archive + network first.
4
Standby wallet golden rule?
Wallet on the standby before any MEK op; run key ops on the primary only; re-sync after every op.
5
Free HW crypto on AIX/POWER?
Don't assume it — it's RU-dependent. Benchmark the encryption overhead in the pilot.
6
Are new tablespaces auto-encrypted?
Set ENCRYPT_NEW_TABLESPACES=ALWAYS. Note: encrypted blocks don't compress — re-size RMAN backups.

## Slide 23
HOW WE TAKE IT TO THE FLEET
Rollout: pilot-first, in waves
Pilot
DEV
TEST
PREPROD
PROD
Each wave gated by the previous wave's exit criteria · batched 10–20 DBs · TLS and TDE progress independently
Pilot proves & measures
2–3 representative DBs (CDB, non-CDB, one with DG)
Capture TDE performance baselines on POWER
Prove runbooks and rollback at least once
The long pole (TLS)
App truststore + connect-string migration
Runs in parallel via dual-port coexistence
Start early — it sets the PROD timeline
Cross-cutting gates
Data Guard health green before & after
Keystore backup verified after every key op
Cert expiry monitoring live before TCPS
Notes: Delivery is pilot-first, then environment waves, each gated by the last. Two things to internalise. First, the pilot's real job isn't just proving runbooks — it's capturing the AIX/POWER performance baseline before we commit the fleet. Second, on the TLS side the application migration is the long pole; it runs in parallel under coexistence but it, not the DBA work, sets the production timeline. The right-hand gates apply to every wave: DG health, keystore backups, cert monitoring.

## Slide 24
IN SUMMARY
Two controls, two tracks, one disciplined rollout
TLS runbook + scripts complete; verified live
Reversible · dual-port coexistence · app migration is the long pole
TDE chain verified on 19.27; AIX items open
Forward-only · start local → OKV · keys are the crown jewels
IMMEDIATE NEXT STEPS
1
Select & schedule the pilot — 2–3 representative DBs on prod-class POWER hardware
2
Confirm CA SAN process — Template that stamps CN=FQDN + DNS SANs; agree CSR SLA
3
Decide ANO interim & OKV — Sponsor calls: quick-win native encryption; OKV licensing
4
Engage app teams now — Kick off truststore + connect-string migration — the long pole
Documentation: docs/00–04 · Scripts: scripts/tls · scripts/tde · scripts/dg
Notes: Pull it together. Both tracks have documented runbooks and script templates; TLS is verified live and TDE's chain is verified on 19.27 with the AIX-specific items deliberately deferred to the pilot. The four next steps are what unblocks production: schedule the pilot on real POWER hardware, confirm the CA can do SANs, get sponsor decisions on the native-encryption interim and OKV, and get the app teams moving now because they're the long pole. Then take questions.